## Sheet2
Health Care Governing Board Planning Calendar
2024
| Jan | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec
Human Resources
Fill in timeline/dates using blue fill
Open Enrollment
Plan design - finalized | June: 2024-06-30
System configuration and testing | bar: July to Nov
Finalize rates and materials | bar: Oct to Nov
Open enrollment period | bar: Nov
Finalization and integration to vendors | bar: Dec
Bargaining concepts & costing | bar: June to July
Bargaining authority | bar: July to August
Contract negotiation | bar: July to Dec
OPEIU determination to join benefits | bar: Oct
Finance
Budget Requests Due to Budget Office | July: 2024-07-19
Budget Committee Review/Balancing | bar: August
Budget Book Prep | bar: Sept
City Manager's Recommended Budget | Oct: 2024-10-01
Davison & Associates
Updated Benchmarking | bar: Feb to March
Employee Contribution Change Discussion | bar: Feb to May
Plan Change Discussion | bar: Feb to June
FTE Change Discussion | bar: Feb to June
Carrier Utilization Reviews | Feb: Kaiser - Completed in February; June: Regence - scheduled in June
Regence Self-Funded Plan Projections | bar: June to Oct
Kaiser Renewal | July: July 1
Plug in final Kaiser options | bar: July to August
Plug in Regence options | bar: July to Oct
Plug in contribution options | bar: July to Oct
Market Stop Loss | bar: August
Regence ASO Renewal and Summary of Changes | bar: August to Sept
Stop Loss Decision - Finalize Rates Using Claims Data thru August | Sept: September 16-27
Stop Loss Decision - Finalize Rates Using Claims Data thru September | Oct: October 14-25
Legal
Fill in timeline/dates using yellow fill
Other
Fill in timeline/dates using gray fill